## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Product Backlog
| Table 1 | Product Backlog
Sprint Backlog
| Table 1 | Sprint Backlog
Stand up Meeting
| Table 1 | Stand up Meeting
Retrospection
| Table 1 | Retrospection

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 |  | Studied the fundamentals of Machine Learning, Deep Learning, neural networks, Transformers, and LLMs, including their types, architectures, working principles, and evolution. | SHOULD HAVE |  | Rajalakshmi Ma’am | 3- Completed
2 | 2 |  | Prepared a detailed report on Machine Learning, Deep Learning, Transformers, and LLMs, covering their types, architectures, working principles, and evolution. | MUST HAVE | 1 | Rajalakshmi Ma’am | 3- Completed
3 | 3 |  | Prepared for a Q&A session on Machine Learning, Deep Learning, Transformers, and LLMs, and answered questions to demonstrate conceptual understanding of the topics. | MUST HAVE | 1 | Rajalakshmi Ma’am | 3- Completed
4 | 4 |  | Collected and organized annual reports from multiple companies for 2023, 2024, and 2025 to support financial document analysis for the multi-agent AI research project. | MUST HAVE |  | Rajalakshmi Ma’am | 3- Completed
5 | 5 |  | Designed the multi-agent architecture and developed research session management, Document Agent, and Extraction Agent. | MUST HAVE | 4 | Rajalakshmi Ma’am | 3- Completed
6 | 6 |  | Developed Red Flag, Research, and Comparison Agents, implemented multi-agent orchestration, validated outputs, and began chat interface and report generation. | MUST HAVE | 5 | Rajalakshmi Ma’am | 3- Completed
7 | 7 |  | Completed the Report Agent, conducted end-to-end testing, and optimized prompts, retrieval quality, and multi-agent orchestration. | MUST HAVE | 6 | Rajalakshmi Ma’am | 2- In Progress
Note on F1: : ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Build
Build
Build
Build
Build
|  |  |  | Build |  | Build
|  |  |  | Build |  | Build
|  |  |  | Build |  | Build
|  |  |  | Build |  | Build
|  |  |  | Build |  | Build
|  |  |  | Build |  | Build
|  |  |  | Build |  | Build
|  |  |  | Build |  | Build
|  |  |  | Build |  | Build
|  |  |  | Build |  | Build
|  |  |  | Build |  | Build
|  |  |  | Build |  | Build
|  |  |  | Build |  | Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Build
Note on D2: : ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: : ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: : ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: : ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: : ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: : ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: : ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: : ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: : ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: : ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: : ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: : ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: : ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: : ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: : ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: : ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: : ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7